## Bike projects
10 Year Capital Works Program for Bike Projects |  |  |  | Key | External | Co-funded | Construct | Design
Suburb | Project | Type | Description | 2022_23 One | 2023_24 Two | 2024_25 Three | 2025_26 Four | 2026_27 Five | 2027_28 Six | 2028_29 Seven | 2029_30 Eight | 2030_31 Nine | 2031_32 Ten
All | Minor infrastructure works and planning |  | Small infrastructure and planning for future works (e.g. bollards, small concrete works, design work), Post Implementation engagement activities | 150257 | 7267 | 11764 | 136545 | 119815 | 53722 | 68053 | 63020 | 228486 | 94456
All | Annual Bicycle Parking | Bicycle Parking | Provide bike parking for at least 200 bikes per annum | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000
Pascoe Vale | Craigieburn Shared Path - Devon Road to Bothwell Street | New Shared Path | Off street shared path adjacent to Craigieburn Railway. | 50000 |  |  | External Funding Obtained
Pascoe Vale | Craigieburn Shared Path - Bothwell Street to Gaffney Street | New Shared Path | Off road shared path adjacent to Craigieburn Railway. | External Funding Obtained
Glenroy | Craigieburn Shared Path (Stage 4) - Glenroy Road to Barina Street (link to LXRP works at activity centre) | New Shared Path | 1km - 3m wide shared path adjacent to Craigieburn Railway. Retaining wall at southern section | 40000 | 700000
Glenroy | Craigieburn Shared Path - Linking Western Ring Road Trail to Glenroy activity centre (dependant on LXRP works) | New Shared Path | 800m long - 3m wide - Concrete shared path. Pole mounted solar lights |  |  |  | 50000 |  | 1000000
Brunswick | Dawson Street separated bike Lanes - Upfield Path to Barry Street | separated on-road bike lanes | Install barrier treatments between car and bike lane | 100000
Pascoe Vale | O'Hea Street Bike Path Extension - Sussex to Derby Street | Separated on-road Bike Lanes | 300m of barrier treatments between car and bike lane. Modification of Sussex Street traffic signals | 50000 |  | 650000
Coburg | Harding Street Bridge Replacement for the Merri Creek Trail | Bridge and access paths | Construct a new bridge over Merri Creek and upgrade access paths linking bridge to Harding Street, Kendall St and Merri Creek Trail | 30000 | Seek external funding
Coburg | De Carle Street separated Bike Lanes - The Avenue to Moreland Road | De Carle separated lanes | Separated lanes from The Avenue to Moreland Road | Carry Forward Funding Obtained
| Additional Staff |  | Engagement officer | 120000
Fawkner | Fawkner Cycling Route(s) | Intersection upgrade, Bicycle Wayfinding | Consult with the Fawkner community to work out preferred cycling route(s) and infrastructure required to support these routes (additional funding likely required once projects are known)
Brunswick East | Lygon St - Capital City Trail Crossing | Intersection Upgrade | Upgrade crossing to manage high volumes of pedestrians and cyclists |  | 50000
Brunswick | Albert to Wilkinson Street Path Widening and Refuge Island - Upfield Shared Path Upgrade | Refuge Island | Refuge island on Albert Street, Brunswick. Path widening from Albert Street to Wilkinson Street |  |  | 50000 | 250000
Brunswick West | Hopetoun Bridge to Moreland Road Shared Path - Increase access to the Moonee Ponds Creek - island on Moreland Road | New Shared Path | 200m long - 3m wide - Connect the new bridge across the Moonee Ponds Creek to Moreland Road Via the Hopetoun Avenue |  | 40000 | 200000
Brunswick East | Merri Trail - Sumner Park to Capital City Trail Flood Mitigation - Bridge across Merri Creek into Darebin | Bridge and access paths | Bridge across Merri Creek into Darebin - Alternative Merri Creek Trail alignment to manage flood risks and soil deposition. Funding allocated for potential works for the flooding on the Moreland side (e.g. boardwalk) | Carry Forward Funding Obtained |  | Additional funding from Council could be required
Pascoe Vale | Reynolds Parade seperated Lanes - York Street Traffic Management - Bell Street intersection Upgrade - Links O'Hea Street to Moonee Ponds Creek Trail via Pascoe Vale. Provides alternative north south route to Melville Road | seperated On-Road Bike Lanes | 830m legth - 300mm wide barrier treatments between car and bike lane Reynolds. Instersection Upgrade Bell Street. Traffic calming on York Street Impact: possible signifcant loss of parking | [8 empty] | 40000 | 500000
Coburg | Batman Avenue Shared Path / shared zone - Upfield shared path upgrade | New Shared Path | 110m path - 3m wide / or shared zone |  |  | 30000 | 180000
Glenroy / Fawkner | Sages Road Shared Path - Upfield Shared Path | New Shared Path | Construct shared path adjacent Sages Rd, Fawkner. Moves a section of Upfield route off mixed traffic street. Improves walking routes to Gowrie Railway Station |  |  | 50000 | Seek external funding
Brunswick | Merri Creek Path Widening - Clara Street (moreland Road underpass) | Upgrade Shared Path | 3m wide path - 100m legth Clara Street - 40m legth widing narrow section of Merri Creek Path. |  | 150000
Pascoe Vale South | CitiLink Shared Path - Moreland Road to Reynard Street - Access to Moonee Ponds Creek Trail via Hoptoun Bridge | Upgrade Shared Path | 3m wide path from Moreland Road to Reynard Street on the east side of CItiLink |  |  | 40000 | 200000
Gowanbrae | Primula Bvd Shared Path (north of Adelaide Bvd) | New Shared Path | 320m - 2.5m wide shared path |  |  |  | 150000
Glenroy | Glenroy Road Shared Path - Cardinal Road to West Street activity centre | New Shared Path | Upgrade Footpath 860m to shared path standard on Glenroy Rd between Cardinal Rd and West St | [7 empty] | 50000 | 700000
Pascoe Vale | Coonans Road seperated Lanes | seperated On-Road Bike Lanes | Install barrier treatments between car and bike lane. Impact: possible signifcant loss of parking | [8 empty] | 40000 | 350000
Brunswick | Victoria Street seperated Lanes - Pearson Street to Upfield SUP | seperated On-Road Bike Lanes | Install barrier treatments between car and bike lane - Pearson Street o Upfield SUP. Impact: signifcant loss of parking | [6 empty] | 80000 | 1000000
Brunswick | Blyth Street Bike Corridor - Sydney Rd to Merri Creek Trail (alternative streets should be considered) | Separated On-Road Bike Lanes | Install barrier treatments between car and bike lane (consider Victoria Street for one direction). Impact: signifcant loss of parking | [8 empty] | 80000
Coburg | Merri Trail Upgrade at Bowden Reserve - Improve access at Bell Street and grade of existing bridge | Boardwalk and access paths | Replace Non-DDA complaint boardwalk, construct new access paths to Nicholson St within Bowden Reserve to bypass flood prone Bell St underpass. | 120000 |  |  |  | 900000
Hadfield | West Street Separated Bike Lanes - Boundary Road to Glenroy Road | separated On-Road Bike Lanes | Separated bike lanes on West Street to local shopping area. Impact: possible signifcant loss of parking | [8 empty] | 50000 | 300000
Pascoe Vale | Kent Road separated Bike Lane - KW Joyce to Cumberland Road NOTE: TO BE CONFIRMED AT MARCH 2022 COUNCIL MEETING | separated On-Road Bike Lanes | Seperated bike lanes Kent Road - links with VicRoads works on Kent Road and Derby Street. Part of the Coburg to Glenroy Link. Impact: traffic lanes reduced to typical local road width | 300000
Fawkner | Fawkner Transport Study | TBD | Engagement to occur during MITS consultation to find walking and cycling projects for Fawkner. Additional funding could be required depending on projects found during consultation |  | 50000 |  | 100000
Brunswick | Glenlyon Road Bike Corridor - Sydney Road to Nicholson Street | TBD | Lower street bike infrastuture creating a major East West route. Could consider alternative parallel street. Impact: possible signifcant loss of parking | [5 empty] | 80000 | 1000000
Coburg | Harding Street Bike Corridor - Sydney Road to Merri Creek Shared Path | TBD | Lower street bike infrastuture creating a major East West route. Could consider alternative parallel street. Impact: possible signifcant loss of parking, blue stone works greatly increases construction cost |  |  |  |  | 80000 |  | External funding likely required
Coburg | Munro Street Bike Corridor - Sydney Road to Rose Street | TBD | Lower street bike infrastuture creating a major East West route. Could consider alternative parallel street. Impact: possible signifcant loss of parking | [8 empty] | 80000 | Unknown
Pascoe Vale | Pascoe Street Bike Shared Path - Boundary Road to West Street to link to Westbreen PS School | seperated On-Road Bike Lanes | Improve bike access from existing shared path to School. | [6 empty] | 20000 | 80000
|  |  |  | 1040257.2 | 1077266.574 | 1111763.9491 | 1146544.6168 | 1179815.2259 | 1213721.5474 | 1248052.7213 | 1273019.6341 | 1298486.0022 | 1324455.7222

## Ped Projects
10 Year Capital Works Program for pedestrians | [5 empty] | Key | External | Co-funded | Construct | Design
Project | Type | Description | 2019_20 | 2020_21 | 2021_22 | 2022_23 | 2023_24 | 2024_25 | 2025_26 | 2026_27 | 2027_28 | 2028_29 | 2029_30 | 2030_31 | 2031_32
Annual DDA Upgrades/Improvements | Footpath Upgrade | Upgrade of the pedestrian network to meet DDA standards | 100000 | 100000 | 102000 | 104040 | 106120.8 | 108243.216 | 110408.0803 | 112616.2419 | 114868.5668 | 117165.9381 | 119509.2569 | 121899.442 | 124337
Annual DDA Upgrades/Improvements at shopping precincts | Footpath Upgrade | Upgrade of the pedestrian network to meet DDA standards around shopping areas | 80000 | 80000 | 81600 | 83232 | 84896.64 | 86594.5728 | 88326.4643 | 90092.9935 | 91894.8534 | 93732.7505 | 95607.4055 | 97519.5536 | 99470
Annual Pedestrian Threshold Treatments | Intersection upgrade | Install threshold treatments to improve pedestrian access and slow traffic | 80000 | 80000 | 81600 | 83232 | 84896.64 | 86594.5728 | 88326.4643 | 90092.9935 | 91894.8534 | 93732.7505 | 95607.4055 | 97519.5536 | 99520
Annual Bus Stop Improvements | Public Transport | Upgrade of bus stops to improve access and provide shelter | 60000 | 60000 | 61200 | 62424 | 63672.48 | 64945.9296 | 66244.8482 | 67569.7452 | 68921.1401 | 70299.5629 | 71705.5541 | 73139.6652 | $74, 582
Annual budget to upgrade roundabouts to improve access for pedestrians and cyclists | Intersection upgrade | Improve road marking/infrastructure for cyclists and pedestrians at existing roundabouts and work to replace the most dangerous existing roundabouts with more appropriate treatments |  |  | 100000 | 102000 | 104040 | 106120.8 | 108243.216 | 110408.0803 | 112616.2419 | 114868.5668 | 117165.9381 | 119509.2569 | 121899
Biennial Pedestrian Operated Signals | New Traffic Signals | Provide safer crossing locations for pedestrians (and sometimes cyclists) |  |  | 40000 | 200000 | 40800 | 204000 | 41616 | 208080 | 42448.32 | 212241.6 | 43297.2864 | 216486.432 | 220816
Stewart Street footpath widening (Nicholson St to Ryan St) | New footpath | New footpath on the southern side |  |  | Design (managed by Urban Design) | Construct (managed by Urban Design)
Zebra Crossings at Intersections | Intersection upgrade | Zebra crossings at intersections to provide pedestrian priority |  |  |  | 50000
Improve link from the Kingfisher Garden bridge to Brunswick East PS | Walking path Upgrade ROW | Walking route via laneway | [5 empty] | 10000 | 100000
New Footpath - Urquhart Street (Elm Grove to Sydney Rd) North Side - likely built by developer | New Footpath | Reconfigure car parking to create space, reconstruct kerb and channel, Construct a footpath near bluestone prison walls on north side of Urquhart St. |  |  |  |  | Construct
Footpath - Pentridge Blvd (Champ Street to Wardens Walk) North side | New Footpath | Construct a footpath near bluestone prison walls on north side of Pentridge Blvd | [8 empty] | Design - seek funding as an separate budget bid | Construct - seek funding as an separate budget bid
|  |  | 320000 | 320000 | 466400 | 684928 | 484426.56 | 666499.0912 | 603165.073 | 678860.0545 | 522643.9756 | 702041.1687 | 542892.8465 | 726073.9033 | 666042